## COVER
TQA Solutions Estimation
Market Place Project
Version 1.0 2024/03/06

## ASSUMPTIONS (hidden)
Market Place Project Assumptions
No | CONTENT |  |  |  | NOTE
1 | Overview
Tạo các hình ảnh cho áp phích bầu cử theo template có sẵn
Có thể chia sẻ hình ảnh lên mạng xã hội (Twitter, Facebook, Instagram, Line), tài liệu in
…
2 | Scope of work
2.1 | Basic Design + UI Design (XD file): Do khách hàng cung cấp đầy đủ trước thời điểm phát triển. |  |  |  | Out of scope
2.2 | Detailed Design: Không cần |  |  |  | Out of scope
2.3 | Coding & Unit Test: Tạo UI từ XD file, phát triển màn hình và kiểm thử đơn vị theo màn hình |  |  |  | Note: Unit test specs with test result in English only.
2.4 | Integration Test: Test tích hợp các màn hình theo business rule |  |  |  | Note: Integration test specs with test result in English only.
2.5 | UAT Support & Final Release: Hỗ trợ khách hàng nghiệm thu sản phẩm theo yêu cầu đã phê duyệt |  |  |  | 1 weeks from UAT release
3 | System approach
3.1 | Framework / Development Language: VueJS 2+, Fabric JS
3.2 | Web Server/ OS: Apache 2.2 / CentOS 7.x or higher |  |  |  | For testing
3.3 | Web Server/ OS: using Amazon web services (AWS), S3, Coud font |  |  |  | For production
4 | Restrictions
4.1 | Support responsive for Mobile device & Web PC/Safari |  |  |  | Lastest stable version
4.2 | Screen size minimum for PC/Mac PC 1366 x 768
4.3 | Mobile support: iPhone 10 or higher; Android 8.0 or higher (Screen size: 6 inch or higher)
4.4 | Production dự kiến: AWS service (VIETIS hỗ trợ dựng và cài đặt application, chi phí vận hành do KH thanh toán riêng)
5 | Deliverables from VietIS
| Tên sản phẩm | Số lượng | Đơn vị | Quy cách
5.1 | Source Package | 1 | Bộ | Deploy trực tiếp lên server của KH
5.2 | Unit Test Report | 1 | Bộ | ZIP file, attach mail
5.3 | Integration Test Report | 1 | Bộ | ZIP file, attach mail
6 | Master Schedule |  |  |  | -
6.1 | Start Date: TBD |  |  |  | TBD = To-Be-Determined
6.2 | Interim Release #1 (Hoàn thành UT) : TBD + 1 weeks (2/6 màn hình) |  |  |  | Vận hành thử trên môi trường test của VIETIS giai đoạn Unit Test
6.3 | Interim Release #2 (Hoàn thành UT) : TBD + 3 weeks (4/6 màn hình)
6.4 | UAT Release (hoàn thành IT): TBD + 4 weeks |  |  |  | Trường hợp khách hàng không bố trí được thời gian nghiệm thu trong phạm vi lịch đã định mà không do phía VIETIS thì sản phẩm được coi là đã nghiệm thu và chuyển sang giai đoạn bảo hành.
6.5 | UAT Support and Final Release (End Date): TBD + 6 weeks
7 | Maintenance & Warranty |  |  |  | "Change request" được hiểu là những yêu cầu thay đổi từ phía khách hàng so với yêu cầu đã được 2 bên thống nhất. "Bug" được hiểu là lỗi sản phẩm so với yêu cầu đã được 2 bên thống nhất (Trường hợp giữa các requirement của khách hàng có mâu thuẫn, dẫn tới không thể đáp ứng được tất cả thì không coi là bug)
7.1 | Bảo hành 6 tháng cho bug sản phẩm kể từ ngày nghiệm thu sản phẩm
7.2 | Hỗ trợ miễn phí các change request trong giới hạn sau, tùy trường hợp nào đến trước
a. Change request với tổng effort trong phạm vi [5 man.day] (tính từ thời điểm chốt scope công việc)
b. Trong phạm vi [10 working days] kể từ ngày nghiệm thu sản phẩm.
8 | Trách nhiệm phía VIETIS
8.1 | Cam kết bảo mật tài sản thông tin của khách hàng.
8.2 | Thực hiện công việc theo kế hoạch đã cam kết.
8.5 | Gửi báo cáo status hàng tuần vào thứ 2 cho khách hàng thông qua Email.
8.6 | Meeting hàng tuần với KH theo thời gian quy định khi start dự án.
8.7 | Feedback trong vòng 1 ngày làm việc với các request từ phía khách hàng
9 | Trách nhiệm phía khách hàng
9.1 | Review & approve về kế hoạch dự án.
9.2 | Cung cấp đầy đủ các tài liệu input trước thời điểm start dự án 03 ngày.
9.3 | Trả phí bản quyền, phí thuê/mua các tài sản/dịch vụ phục vụ dự án theo kế hoạch dự án
9.4 | Nghiệm thu sản phẩm dựa trên requirement đã cung cấp trong vòng 2 tuần
9.5 | Feedback trong vòng 1 working day đối với Q&A từ phía VIETIS trong quá trình thực hiện dự án
10 | Điều kiện nghiệm thu, thanh toán và thay đổi scope
10.1 | Tiêu chuẩn nghiệm thu. |  |  |  | Trường hợp các yêu cầu có mâu thuẫn, dẫn đến không thể đáp ứng được tất cả thì sẽ ko tính các yêu cầu không đáp ứng này vào mức độ hoàn thành.
a. Hoàn thành 100% yêu cầu mà hai bên đã thống nhất trong tài liệu 20/10/2022
b. Không còn bug phát sinh sau khi khách hàng đã hoàn thành test nghiệm thu theo kế hoạch đã định trong mục 9.4
c. Complete toàn bộ các task được giao trong thời hạn thực hiện dự án với số lỗi = 0.
10.2 | Trường hợp có bất cứ sự thay đổi nào về scope công việc và assumption nêu trên, hai bên cần bàn bạc và re-estimate lại cho phù hợp.

## ESTIMATION SUMMARY (Ext) (hidden)
Market Place Project WBS Estimation
| No | Work Content |  |  | Effort (man.month) | Unit Cost (ManJPY/mm) | Total Cost (Man JPY) | Note
| 1 | Project Preparation |  |  | 0.1 | 45 | 4.5 | 1 person x 2 days
| 2 | Development Effort |  |  | 15.49 |  | 604.11
| 2.1 | Requirement Definition |  |  | 0 |  | 0 | 0% | of development Effort
| 2.2 | Basic Design |  |  | 0 |  | 0 | 0% | of development Effort
| 2.3 | Detail Design |  |  | 0 |  | 0 | 0% | of development Effort
| 2.4 | Coding |  |  | 11.25 | 39 | 438.75 | 65% | of development Effort
| 2.5 | Unit Test |  |  | 3.03 | 39 | 118.17 | 25% | of development Effort
| 2.6 | Integration Test |  |  | 1.21 | 39 | 47.19 | 10% | of development Effort
| 2.7 | System Test |  |  | 0 |  | 0 | 0% | of development Effort
| 3 | Overhead Effort for Communication & Management |  |  | 2.63 | 45 | 118.35 | 17% | of total development Effort
| TOTAL EFFORT |  |  |  | 18.22 |  | 726.96
|  | Development Scope |  | Management Scope
|  | Scope | CD-UT-IT | Daily Report |  |  | No
|  | Basic Design | - | Daily Meeting |  |  | No
|  | Detail Design | - | Weekly Report |  |  | Yes
|  | UT Evident | Not-Included | Weekly Meeting |  |  | Yes
|  | IT Evident | Not-Included | Estimation Method |  |  | Complex Level
Note: [-] Select for out-of-scope

## ESTIMATION SUMMARY
Market Place Project WBS Estimation (Internal)
| No | Work Content |  |  | Effort (man.month) | Unit Cost (ManVND/mm) | Total Cost (Man VND) | Note
| 1 | Project Preparation |  |  | 0.1 | 40000000 | 4000000 | 1 person x 2 days
| 2 | Development Effort |  |  | 19.01 |  | 635050000
| 2.1 | Requirement Definition |  |  | 0 |  | 0 | 0% | of development Effort
| 2.2 | UI Layout Design (Not Detail by Figma) |  |  | 1.5 | 35000000 | 52500000 | 0% | of development Effort
| 2.3 | Basic Design (DB Design, Infra Design) |  |  | 0.2 | 35000000 | 7000000 | 0% | of development Effort
| 2.4 | Detail Design |  |  | 0 |  | 0 | 0% | of development Effort
| 2.5 | Coding |  |  | 11.25 | 35000000 | 393750000 | 65% | of development Effort
| 2.6 | Unit Test |  |  | 4.33 | 30000000 | 129900000 | 25% | of development Effort
| 2.7 | Integration Test |  |  | 1.73 | 30000000 | 51900000 | 10% | of development Effort
| 2.8 | System Test |  |  | 0 |  | 0 | 0% | of development Effort
| 3 | Overhead Effort for Communication & Management |  |  | 3.23 | 40000000 | 129200000 | 17% | of total development Effort
| TOTAL EFFORT |  |  |  | 22.34 |  | 768250000
|  | Development Scope |  | Management Scope
|  | Scope | CD-UT-IT | Daily Report |  |  | No
|  | Basic Design | - | Daily Meeting |  |  | No
|  | Detail Design | - | Weekly Report |  |  | Yes
|  | UT Evident | Not-Included | Weekly Meeting |  |  | Yes
|  | IT Evident | Not-Included | Estimation Method |  |  | Complex Level
Note: [-] Select for out-of-scope

## ESTIMATION (Complex Level)
Market Place Project WBS Detailed Estimation
Coding effort unit: person.days
| No | Requirement List |  |  | Complex Level | Coding Effort | %Reuse | TOTAL CODING EFFORT | Note
|  | Code | Name
| 1 | 001 | Init source + database |  |  | 4 |  | 4
| 3 | 003 | Authentication |  |  |  |  | 0
| 4 | 004 |  | Đăng nhập |  | 0.5 |  | 0.5
| 5 | 005 |  | Đăng kí |  | 0.5 |  | 0.5
| 6 | 006 |  | Quên mật khẩu |  | 0.5 |  | 0.5
| 7 | 007 |  | Thay đổi mật khẩu |  | 0.5 |  | 0.5
| 8 | 008 |  | Quản lý thiết bị đăng nhập |  | 2 |  | 2
| 9 | 009 | Khoá học |  |  |  |  | 0
| 10 | 010 |  | Hiển thị danh sách khóa học |  | 2 |  | 2
| 11 | 011 |  | Màn hình hiển thị danh sách bài tập theo từng tuần thi |  | 4 |  | 4
| 12 | 012 |  | Màn hình test preview cho homework |  | 4 |  | 4
| 13 | 013 |  | Màn hình test ( R&W , Math, homework) |  | 8 |  | 8
| 14 | 014 |  | Màn hình check your work (overview) |  | 6 |  | 6
| 15 | 015 |  | Màn hình show test finished |  | 6 |  | 6
| 16 | 016 | Test Result |  |  |  |  | 0
| 17 | 017 |  | Màn hình result cho khóa học thường |  | 6 |  | 6
| 18 | 018 |  | Màn hình result cho lớp ôn đề |  | 6 |  | 6
| 19 | 019 | Quản lý khóa học |  |  |  |  | 0
| 20 | 020 |  | Thêm, sửa, xóa khóa học |  | 8 |  | 8
| 21 | 021 |  | Thêm học viên vào khóa học |  | 6 |  | 6
| 22 | 022 |  | Thêm Assign expiration date cho khóa học |  | 4 |  | 4
| 23 | 023 |  | Quản lý danh sách category (lớp nhỏ) của khóa học |  | 4 |  | 4
| 24 | 024 |  | Quản lý danh sách tuần học theo category (lớp nhỏ) |  | 4 |  | 4
| 25 | 025 |  | Quản lý danh sách bài tập theo tuần |  | 6 |  | 6
| 26 | 026 | Quản lý học viên |  |  |  |  | 0
| 27 | 027 |  | Màn hình hiển thị danh sách học viên |  | 6 |  | 6
| 28 | 028 |  | Cập nhật profile học viên ( họ tên, trạng thái, .... ) |  | 4 |  | 4
| 29 | 029 |  | Màn hình xem profile học viên |  | 4 |  | 4
| 30 | 030 |  | Tracking lịch sử đăng nhập của học viên |  | 4 |  | 4
| 31 | 031 |  | Cập nhật thiết bị mới cho học viên |  | 3 |  | 3
| 32 | 032 | Quản lý thư viện câu hỏi |  |  |  |  | 0
| 33 | 033 |  | Upload câu hỏi theo file word (Giữ được format) |  | 8 |  | 8
| 34 | 034 |  | Chức năng nhập câu hỏi thủ công theo bài tập |  | 10 |  | 10
| 35 | 035 | Learning Screen |  |  |  |  | 0
| 36 | 036 |  | Video bài giảng |  | 8 |  | 8
| 37 | 037 |  | Popup questions trong video |  | 4 |  | 4
| 38 | 038 |  | Practice set (sau video) |  | 8 |  | 8
| 39 | 039 |  | Mini Checkpoint |  | 4 |  | 4
| 40 | 040 |  | Question Difficulty & Scoring |  | 6 |  | 6
| 41 | 041 | Personalization |  |  |  |  | 0
| 42 | 042 |  | Learning Mode (AI) |  | 10 |  | 10
| 43 | 043 |  | Test Mode |  | 6 |  | 6
| 44 | 044 | Checkpoint |  |  |  |  | 0
| 45 | 045 |  | Điểm danh giữ chuỗi theo ngày |  | 2 |  | 2
| 46 | 046 |  | Dash board: Top 10 HS xuất sắc nhất tuần |  | 4 |  | 4
| 47 | 047 |  | Push noti: Gửi email nhắc nhở nếu HS không đăng nhập vào học quá 1 ngày, 1 tuần, 1 tháng. |  | 4 |  | 4
| 48 | 048 | Tính năng bổ trợ |  |  |  |  | 0
| 49 | 049 |  | Sổ tay cá nhân |  | 6 |  | 6
| 50 | 050 |  | Chat GPT hoặc Gemini tích hợp vào web |  | 6 |  | 6
| 51 | 051 |  | Highlight đoạn văn bản/từ vựng -> hỏi AI -> Tiết kiệm tgian copy-paste |  | 10 |  | 10
| 52 | 052 |  | Trial: Học thử 1-2 section |  | 8 |  | 8
| 53 | 053 | Cổng thanh toán trực tuyến |  |  | 10 |  | 10
| 54 | 054 | Hỗ trợ sale & CSKH |  |  |  |  | 0
| 55 | 055 |  | Nút book lịch tư vấn với mentor |  | 2 |  | 2
| 56 | 056 |  | Nút join cộng đồng học tập |  | 2 |  | 2
| 57 | 057 |  | Download report học tập |  | 4 |  | 4
| TOTAL | [6 empty] | 225

## ESTIMATION (LOC) (hidden)
Market Place Project WBS Detailed Estimation (LOC)
| No | Requirement List |  |  | #Screen Item | #Logic Steps | #Table Items | Estimated LOC | %Reuse | Coding Effort | Note
|  | Code | Name | Technical
| 1 | RQ-001 | <Mô tả chức năng/màn hình ở đây> | JAVA | 2 | 10 | 6 | 322 |  | 3.6 | <note here if any>
| 2 | RQ-002 | <Mô tả chức năng/màn hình ở đây> | JAVA | 10 | 15 | 8 | 465 |  | 5.2 | <note here if any>
| 3 | RQ-003 | <Mô tả chức năng/màn hình ở đây> | JAVA | 1 | 4 | 5 | 216 |  | 2.4 | <note here if any>
| 4 | RQ-004 | <Mô tả chức năng/màn hình ở đây> | JAVA | 2 | 3 | 0 | 157 | 20% | 1.4 | <note here if any>
| 5 | RQ-005 | <Mô tả chức năng/màn hình ở đây> | JAVA | 2 | 1 | 4 | 167 | 20% | 1.5 | <note here if any>
| 6 | RQ-006 | <Mô tả chức năng/màn hình ở đây> | JAVA | 3 | 2 | 4 | 188 | 20% | 1.7 | <note here if any>
| 7 | RQ-007 | <Mô tả chức năng/màn hình ở đây> | JAVA | 1 | 2 | 1 | 146 |  | 1.6 | <note here if any>
| 8 | RQ-008 | <Mô tả chức năng/màn hình ở đây> | JAVA | 2 | 10 | 6 | 322 |  | 3.6 | <note here if any>
| 9 | RQ-009 | <Mô tả chức năng/màn hình ở đây> | JAVA | 10 | 15 | 8 | 465 |  | 5.2 | <note here if any>
| 10 | RQ-010 | <Mô tả chức năng/màn hình ở đây> | JAVA | 1 | 4 | 5 | 216 |  | 2.4 | <note here if any>
| 11 | RQ-011 | <Mô tả chức năng/màn hình ở đây> | JAVA | 2 | 3 | 0 | 157 |  | 1.7 | <note here if any>
| 12 | RQ-012 | <Mô tả chức năng/màn hình ở đây> | JAVA | 2 | 1 | 4 | 167 |  | 1.9 | <note here if any>
| 13 | RQ-013 | <Mô tả chức năng/màn hình ở đây> | JAVA | 3 | 2 | 4 | 188 |  | 2.1 | <note here if any>
| 14 | RQ-014 | <Mô tả chức năng/màn hình ở đây> | C# | 1 | 2 | 1 | 146 |  | 1.3 | <note here if any>
| 15 | RQ-015 | <Mô tả chức năng/màn hình ở đây> | C# | 2 | 10 | 6 | 322 |  | 2.8 | <note here if any>
| 16 | RQ-016 | <Mô tả chức năng/màn hình ở đây> | C# | 10 | 15 | 8 | 465 |  | 4 | <note here if any>
| 17 | RQ-017 | <Mô tả chức năng/màn hình ở đây> | C# | 1 | 4 | 5 | 216 |  | 1.9 | <note here if any>
| 18 | RQ-018 | <Mô tả chức năng/màn hình ở đây> | C# | 2 | 3 | 0 | 157 |  | 1.4 | <note here if any>
| 19 | RQ-019 | <Mô tả chức năng/màn hình ở đây> | C# | 2 | 10 | 6 | 322 |  | 2.8 | <note here if any>
| 20 | RQ-020 | <Mô tả chức năng/màn hình ở đây> | C# | 10 | 15 | 8 | 465 |  | 4 | <note here if any>
| 21 | RQ-021 | <Mô tả chức năng/màn hình ở đây> | C# | 1 | 4 | 5 | 216 |  | 1.9 | <note here if any>
| 22 | RQ-022 | <Mô tả chức năng/màn hình ở đây> | C# | 2 | 3 | 0 | 157 |  | 1.4 | <note here if any>
| 23 | RQ-023 | <Mô tả chức năng/màn hình ở đây> | C# | 2 | 1 | 4 | 167 |  | 1.5 | <note here if any>
| 24 | RQ-024 | <Mô tả chức năng/màn hình ở đây> | C# | 3 | 2 | 4 | 188 |  | 1.6 | <note here if any>
| 25 | RQ-025 | <Mô tả chức năng/màn hình ở đây> | Others | 1 | 2 | 1 | 146 |  | 1.1 | <note here if any>
| 26 | RQ-026 | <Mô tả chức năng/màn hình ở đây> | Others | 1 | 4 | 5 | 216 |  | 1.7 | <note here if any>
| 27 | RQ-027 | <Mô tả chức năng/màn hình ở đây> | Others | 2 | 3 | 0 | 157 |  | 1.2 | <note here if any>
| 28 | RQ-028 | <Mô tả chức năng/màn hình ở đây> | Others | 2 | 1 | 4 | 167 |  | 1.3 | <note here if any>
| 29 | RQ-029 | <Mô tả chức năng/màn hình ở đây> | Others | 3 | 2 | 4 | 188 |  | 1.4 | <note here if any>
| 30 | RQ-030 | <Mô tả chức năng/màn hình ở đây> | Others | 1 | 2 | 1 | 146 |  | 1.1 | <note here if any>
| TOTAL | [6 empty] | 7017 |  | 66.7

## METRICS (hidden)
Market Place Project Estimation Metrics
1 | Parameter for estimate for Line-Of-Code estimation | [6 empty] | Unit: person.days
| No | Parameters |  | Parameter Description |  | Standard Value | Adjusted Value | Unit
| 1 | Average common LOC |  | Common processing for each screen/function |  | 100 | - | LOC
| 2 | Average LOC for each Screen Item |  | - |  | 6 | - | LOC/Item
| 3 | Average LOC for each Logic Step |  | - |  | 15 | - | LOC/Item
| 4 | Average LOC for each Table Fields |  | - |  | 10 | - | LOC/Item
2 | Non-Functional Adjustment Factors
| No | Non-Functional Requirement Factors | Adjustment Decision | Adjustment Rate | Adjustment Reasons
| 1 | Usability | - | - | -
| 1.1 | User Interface Friendly | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| 1.2 | UI Environment Test | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| 2 | Availability | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| 3 | Performance | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| 4 | Business Rule & Regulation | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| 5 | Technology Used | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| 6 | Interface with other systems | Normal | 1 | <Tham khảo guideline khi thay đổi giá trị và note rõ lý do thay đổi>
| Adjustment Summary |  |  | 1 | -

## INTERNAL ESTIMATION (hidden)
Market Place Project Internal Estimation
Đây là sheet estimation effort cho nội bộ, không dùng để gửi cho khách hàng.
| Adjustment Factors |  | Unit: Man.Months
|  | External Estimation |  | 22.34
|  | Development |  | 19.01 | (From Estimation Summary)
|  | Preparation & Overhead Management |  | 3.33 | (From Estimation Summary)
|  | Internal Estimation |  | 25.7346
|  | Development |  | 22.4046 | Adjust by Technology/Business & Resource Skill. Refere guideline for more detail.
|  | Preparation & Overhead Management |  | 3.33 | (From Estimation Summary)
|  | a) Technology / Business |  | 2-Ít quen thuộc |  |  |  |  | Rate: | 1.1
|  |  | Tech Business |  | Quen thuộc |  | Ít quen thuộc |  | Không quen thuộc
|  |  | Quen thuộc |  | Quen thuộc |  | Quen thuộc |  | Ít quen thuộc
|  |  | Ít quen thuộc |  | Quen thuộc |  | Ít quen thuộc |  | Ít quen thuộc
|  |  | Không quen thuộc |  | Ít quen thuộc |  | Ít quen thuộc |  | Không quen thuộc
|  | b) Resource Skill | [6 empty] | Rate: | 1.0714
Enter Detailed Calendar Resource Skill to calculate Skill Rate (not include PM/Comtor)
|  | Member / Skill Table | %Usage | <Month#1> | <Month#2> | <Month#3> | <Month#4> | <Month#5> | <Month#6> | <Month#7> | Skill 3 | Skill 2 | Skill 1
|  | <Member#1> | 50% | Skill 3 | Skill 3 | Skill 3 | Skill 3 | Skill 3 | Skill 3 | Skill 3 | 3.5 | 0 | 0
|  | <Member#2> | 50% | Skill 2 | Skill 2 | Skill 2 | Skill 2 | Skill 2 | Skill 2 | Skill 2 | 0 | 3.5 | 0
|  | <Member#3> | 100% | Skill 1 | Skill 1 | Skill 1 | Skill 2 | Skill 2 | Skill 2 | Skill 2 | 0 | 4 | 3
|  | <Member#4> | 100% | Skill 1 | Skill 1 | Skill 1 | Skill 2 | Skill 2 | Skill 2 | Skill 2 | 0 | 4 | 3
|  | <Member#5> | 100% | Skill 1 | Skill 1 | Skill 1 | Skill 1 | Skill 1 | Skill 2 | Skill 2 | 0 | 2 | 5
|  | <Member#6> | 100% | Skill 1 | Skill 1 | Skill 1 | Skill 1 | Skill 1 | Skill 2 | Skill 2 | 0 | 2 | 5
|  | <Member#7> | [8 empty] | 0 | 0 | 0
|  | <Member#8> | [8 empty] | 0 | 0 | 0
|  | <Member#9> | [8 empty] | 0 | 0 | 0
|  | <Member#10> | [8 empty] | 0 | 0 | 0
|  | <Member#11> | [8 empty] | 0 | 0 | 0
|  | <Member#12> | [8 empty] | 0 | 0 | 0 | TOTAL
|  | Skill 1: Fresher; Skill 2: BA / Designer / Developer / Tester; Skill 3: BA Lead / Technical Leader | [8 empty] | 3.5 | 15.5 | 16 | 35
[11 empty] | 2.8 | 15.5 | 19.2 | 37.5

## NORMS (hidden)
VIETIS's NORM 2022-S2
Effort distribution by Process
Scope | BD | DD | UT-Evident | IT-Evident | Key | %RQ | %BD | %DD | %CD | %UT | %IT | %ST | Note | TOTAL | Remain with norm
RQ-BD-DD-CD-UT-IT-ST | Detailed | Detailed | Included | Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Detailed.Included.Included | 5% | 6% | 14.28% | 39.48% | 16.8% | 13.44% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Detailed | Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Detailed.Included.Not-Included | 5% | 6% | 15.12% | 40.32% | 18.48% | 10.08% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Detailed | Not-Included | Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Detailed.Not-Included.Included | 5% | 6% | 15.96% | 42% | 13.44% | 12.6% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Detailed | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Detailed.Not-Included.Not-Included | 5% | 6% | 16.8% | 44.52% | 14.28% | 8.4% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Outline | Included | Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Outline.Included.Included | 5% | 6% | 5.88% | 42% | 23.52% | 12.6% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Outline | Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Outline.Included.Not-Included | 5% | 6% | 6.72% | 42.84% | 25.2% | 9.24% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Outline | Not-Included | Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Outline.Not-Included.Included | 5% | 6% | 6.72% | 48.72% | 16.8% | 11.76% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Detailed | Outline | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Detailed.Outline.Not-Included.Not-Included | 5% | 6% | 6.72% | 55.44% | 15.12% | 6.72% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 84%
RQ-BD-DD-CD-UT-IT-ST | Outline | Detailed | Included | Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Detailed.Included.Included | 5% | 4% | 14.62% | 40.42% | 17.2% | 13.76% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Detailed | Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Detailed.Included.Not-Included | 5% | 4% | 15.48% | 41.28% | 18.92% | 10.32% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Detailed | Not-Included | Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Detailed.Not-Included.Included | 5% | 4% | 16.34% | 43% | 13.76% | 12.9% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Detailed | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Detailed.Not-Included.Not-Included | 5% | 4% | 17.2% | 45.58% | 14.62% | 8.6% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Outline | Included | Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Outline.Included.Included | 5% | 4% | 6.02% | 43% | 24.08% | 12.9% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Outline | Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Outline.Included.Not-Included | 5% | 4% | 6.88% | 43.86% | 25.8% | 9.46% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Outline | Not-Included | Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Outline.Not-Included.Included | 5% | 4% | 6.88% | 49.88% | 17.2% | 12.04% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT-ST | Outline | Outline | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT-ST.Outline.Outline.Not-Included.Not-Included | 5% | 4% | 6.88% | 56.76% | 15.48% | 6.88% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 86%
RQ-BD-DD-CD-UT-IT | Detailed | Detailed | Included | Included | RQ-BD-DD-CD-UT-IT.Detailed.Detailed.Included.Included | 5% | 6% | 15.13% | 41.83% | 17.8% | 14.24% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Detailed | Included | Not-Included | RQ-BD-DD-CD-UT-IT.Detailed.Detailed.Included.Not-Included | 5% | 6% | 16.02% | 42.72% | 19.58% | 10.68% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Detailed | Not-Included | Included | RQ-BD-DD-CD-UT-IT.Detailed.Detailed.Not-Included.Included | 5% | 6% | 16.91% | 44.5% | 14.24% | 13.35% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Detailed | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT.Detailed.Detailed.Not-Included.Not-Included | 5% | 6% | 17.8% | 47.17% | 15.13% | 8.9% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Outline | Included | Included | RQ-BD-DD-CD-UT-IT.Detailed.Outline.Included.Included | 5% | 6% | 6.23% | 44.5% | 24.92% | 13.35% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Outline | Included | Not-Included | RQ-BD-DD-CD-UT-IT.Detailed.Outline.Included.Not-Included | 5% | 6% | 7.12% | 45.39% | 26.7% | 9.79% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Outline | Not-Included | Included | RQ-BD-DD-CD-UT-IT.Detailed.Outline.Not-Included.Included | 5% | 6% | 7.12% | 51.62% | 17.8% | 12.46% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Detailed | Outline | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT.Detailed.Outline.Not-Included.Not-Included | 5% | 6% | 7.12% | 58.74% | 16.02% | 7.12% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 89%
RQ-BD-DD-CD-UT-IT | Outline | Detailed | Included | Included | RQ-BD-DD-CD-UT-IT.Outline.Detailed.Included.Included | 5% | 4% | 15.47% | 42.77% | 18.2% | 14.56% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Detailed | Included | Not-Included | RQ-BD-DD-CD-UT-IT.Outline.Detailed.Included.Not-Included | 5% | 4% | 16.38% | 43.68% | 20.02% | 10.92% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Detailed | Not-Included | Included | RQ-BD-DD-CD-UT-IT.Outline.Detailed.Not-Included.Included | 5% | 4% | 17.29% | 45.5% | 14.56% | 13.65% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Detailed | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT.Outline.Detailed.Not-Included.Not-Included | 5% | 4% | 18.2% | 48.23% | 15.47% | 9.1% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Outline | Included | Included | RQ-BD-DD-CD-UT-IT.Outline.Outline.Included.Included | 5% | 4% | 6.37% | 45.5% | 25.48% | 13.65% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Outline | Included | Not-Included | RQ-BD-DD-CD-UT-IT.Outline.Outline.Included.Not-Included | 5% | 4% | 7.28% | 46.41% | 27.3% | 10.01% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Outline | Not-Included | Included | RQ-BD-DD-CD-UT-IT.Outline.Outline.Not-Included.Included | 5% | 4% | 7.28% | 52.78% | 18.2% | 12.74% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-BD-DD-CD-UT-IT | Outline | Outline | Not-Included | Not-Included | RQ-BD-DD-CD-UT-IT.Outline.Outline.Not-Included.Not-Included | 5% | 4% | 7.28% | 60.06% | 16.38% | 7.28% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 91%
RQ-DD-CD-UT-IT-ST | - | Detailed | Included | Included | RQ-DD-CD-UT-IT-ST.-.Detailed.Included.Included | 5% | 0% | 15.3% | 42.3% | 18% | 14.4% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Detailed | Included | Not-Included | RQ-DD-CD-UT-IT-ST.-.Detailed.Included.Not-Included | 5% | 0% | 16.2% | 43.2% | 19.8% | 10.8% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Detailed | Not-Included | Included | RQ-DD-CD-UT-IT-ST.-.Detailed.Not-Included.Included | 5% | 0% | 17.1% | 45% | 14.4% | 13.5% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Detailed | Not-Included | Not-Included | RQ-DD-CD-UT-IT-ST.-.Detailed.Not-Included.Not-Included | 5% | 0% | 18% | 47.7% | 15.3% | 9% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Outline | Included | Included | RQ-DD-CD-UT-IT-ST.-.Outline.Included.Included | 5% | 0% | 6.3% | 45% | 25.2% | 13.5% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Outline | Included | Not-Included | RQ-DD-CD-UT-IT-ST.-.Outline.Included.Not-Included | 5% | 0% | 7.2% | 45.9% | 27% | 9.9% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Outline | Not-Included | Included | RQ-DD-CD-UT-IT-ST.-.Outline.Not-Included.Included | 5% | 0% | 7.2% | 52.2% | 18% | 12.6% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT-ST | - | Outline | Not-Included | Not-Included | RQ-DD-CD-UT-IT-ST.-.Outline.Not-Included.Not-Included | 5% | 0% | 7.2% | 59.4% | 16.2% | 7.2% | 5% | RQ 5%, BD 6%; ST 5% | 100% | 90%
RQ-DD-CD-UT-IT | - | Detailed | Included | Included | RQ-DD-CD-UT-IT.-.Detailed.Included.Included | 5% | 0% | 16.15% | 44.65% | 19% | 15.2% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Detailed | Included | Not-Included | RQ-DD-CD-UT-IT.-.Detailed.Included.Not-Included | 5% | 0% | 17.1% | 45.6% | 20.9% | 11.4% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Detailed | Not-Included | Included | RQ-DD-CD-UT-IT.-.Detailed.Not-Included.Included | 5% | 0% | 18.05% | 47.5% | 15.2% | 14.25% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Detailed | Not-Included | Not-Included | RQ-DD-CD-UT-IT.-.Detailed.Not-Included.Not-Included | 5% | 0% | 19% | 50.35% | 16.15% | 9.5% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Outline | Included | Included | RQ-DD-CD-UT-IT.-.Outline.Included.Included | 5% | 0% | 6.65% | 47.5% | 26.6% | 14.25% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Outline | Included | Not-Included | RQ-DD-CD-UT-IT.-.Outline.Included.Not-Included | 5% | 0% | 7.6% | 48.45% | 28.5% | 10.45% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Outline | Not-Included | Included | RQ-DD-CD-UT-IT.-.Outline.Not-Included.Included | 5% | 0% | 7.6% | 55.1% | 19% | 13.3% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
RQ-DD-CD-UT-IT | - | Outline | Not-Included | Not-Included | RQ-DD-CD-UT-IT.-.Outline.Not-Included.Not-Included | 5% | 0% | 7.6% | 62.7% | 17.1% | 7.6% | 0% | RQ 5%, BD 6%; ST 5% | 100% | 95%
BD-DD-CD-UT-IT-ST | Detailed | Detailed | Included | Included | BD-DD-CD-UT-IT-ST.Detailed.Detailed.Included.Included | 0% | 6% | 15.13% | 41.83% | 17.8% | 14.24% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Detailed | Included | Not-Included | BD-DD-CD-UT-IT-ST.Detailed.Detailed.Included.Not-Included | 0% | 6% | 16.02% | 42.72% | 19.58% | 10.68% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Detailed | Not-Included | Included | BD-DD-CD-UT-IT-ST.Detailed.Detailed.Not-Included.Included | 0% | 6% | 16.91% | 44.5% | 14.24% | 13.35% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Detailed | Not-Included | Not-Included | BD-DD-CD-UT-IT-ST.Detailed.Detailed.Not-Included.Not-Included | 0% | 6% | 17.8% | 47.17% | 15.13% | 8.9% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Outline | Included | Included | BD-DD-CD-UT-IT-ST.Detailed.Outline.Included.Included | 0% | 6% | 6.23% | 44.5% | 24.92% | 13.35% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Outline | Included | Not-Included | BD-DD-CD-UT-IT-ST.Detailed.Outline.Included.Not-Included | 0% | 6% | 7.12% | 45.39% | 26.7% | 9.79% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Outline | Not-Included | Included | BD-DD-CD-UT-IT-ST.Detailed.Outline.Not-Included.Included | 0% | 6% | 7.12% | 51.62% | 17.8% | 12.46% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Detailed | Outline | Not-Included | Not-Included | BD-DD-CD-UT-IT-ST.Detailed.Outline.Not-Included.Not-Included | 0% | 6% | 7.12% | 58.74% | 16.02% | 7.12% | 5% | BD 6%; ST: 5% | 100% | 89%
BD-DD-CD-UT-IT-ST | Outline | Detailed | Included | Included | BD-DD-CD-UT-IT-ST.Outline.Detailed.Included.Included | 0% | 4% | 15.47% | 42.77% | 18.2% | 14.56% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Detailed | Included | Not-Included | BD-DD-CD-UT-IT-ST.Outline.Detailed.Included.Not-Included | 0% | 4% | 16.38% | 43.68% | 20.02% | 10.92% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Detailed | Not-Included | Included | BD-DD-CD-UT-IT-ST.Outline.Detailed.Not-Included.Included | 0% | 4% | 17.29% | 45.5% | 14.56% | 13.65% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Detailed | Not-Included | Not-Included | BD-DD-CD-UT-IT-ST.Outline.Detailed.Not-Included.Not-Included | 0% | 4% | 18.2% | 48.23% | 15.47% | 9.1% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Outline | Included | Included | BD-DD-CD-UT-IT-ST.Outline.Outline.Included.Included | 0% | 4% | 6.37% | 45.5% | 25.48% | 13.65% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Outline | Included | Not-Included | BD-DD-CD-UT-IT-ST.Outline.Outline.Included.Not-Included | 0% | 4% | 7.28% | 46.41% | 27.3% | 10.01% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Outline | Not-Included | Included | BD-DD-CD-UT-IT-ST.Outline.Outline.Not-Included.Included | 0% | 4% | 7.28% | 52.78% | 18.2% | 12.74% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT-ST | Outline | Outline | Not-Included | Not-Included | BD-DD-CD-UT-IT-ST.Outline.Outline.Not-Included.Not-Included | 0% | 4% | 7.28% | 60.06% | 16.38% | 7.28% | 5% | BD 4%; ST: 5% | 100% | 91%
BD-DD-CD-UT-IT | Detailed | Detailed | Included | Included | BD-DD-CD-UT-IT.Detailed.Detailed.Included.Included | 0% | 7% | 15.81% | 43.71% | 18.6% | 14.88% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Detailed | Included | Not-Included | BD-DD-CD-UT-IT.Detailed.Detailed.Included.Not-Included | 0% | 7% | 16.74% | 44.64% | 20.46% | 11.16% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Detailed | Not-Included | Included | BD-DD-CD-UT-IT.Detailed.Detailed.Not-Included.Included | 0% | 7% | 17.67% | 46.5% | 14.88% | 13.95% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Detailed | Not-Included | Not-Included | BD-DD-CD-UT-IT.Detailed.Detailed.Not-Included.Not-Included | 0% | 7% | 18.6% | 49.29% | 15.81% | 9.3% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Outline | Included | Included | BD-DD-CD-UT-IT.Detailed.Outline.Included.Included | 0% | 7% | 6.51% | 46.5% | 26.04% | 13.95% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Outline | Included | Not-Included | BD-DD-CD-UT-IT.Detailed.Outline.Included.Not-Included | 0% | 7% | 7.44% | 47.43% | 27.9% | 10.23% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Outline | Not-Included | Included | BD-DD-CD-UT-IT.Detailed.Outline.Not-Included.Included | 0% | 7% | 7.44% | 53.94% | 18.6% | 13.02% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Detailed | Outline | Not-Included | Not-Included | BD-DD-CD-UT-IT.Detailed.Outline.Not-Included.Not-Included | 0% | 7% | 7.44% | 61.38% | 16.74% | 7.44% | 0% | BD 7%; | 100% | 93%
BD-DD-CD-UT-IT | Outline | Detailed | Included | Included | BD-DD-CD-UT-IT.Outline.Detailed.Included.Included | 0% | 5% | 16.15% | 44.65% | 19% | 15.2% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Detailed | Included | Not-Included | BD-DD-CD-UT-IT.Outline.Detailed.Included.Not-Included | 0% | 5% | 17.1% | 45.6% | 20.9% | 11.4% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Detailed | Not-Included | Included | BD-DD-CD-UT-IT.Outline.Detailed.Not-Included.Included | 0% | 5% | 18.05% | 47.5% | 15.2% | 14.25% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Detailed | Not-Included | Not-Included | BD-DD-CD-UT-IT.Outline.Detailed.Not-Included.Not-Included | 0% | 5% | 19% | 50.35% | 16.15% | 9.5% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Outline | Included | Included | BD-DD-CD-UT-IT.Outline.Outline.Included.Included | 0% | 5% | 6.65% | 47.5% | 26.6% | 14.25% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Outline | Included | Not-Included | BD-DD-CD-UT-IT.Outline.Outline.Included.Not-Included | 0% | 5% | 7.6% | 48.45% | 28.5% | 10.45% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Outline | Not-Included | Included | BD-DD-CD-UT-IT.Outline.Outline.Not-Included.Included | 0% | 5% | 7.6% | 55.1% | 19% | 13.3% | 0% | BD 5%; | 100% | 95%
BD-DD-CD-UT-IT | Outline | Outline | Not-Included | Not-Included | BD-DD-CD-UT-IT.Outline.Outline.Not-Included.Not-Included | 0% | 5% | 7.6% | 62.7% | 17.1% | 7.6% | 0% | BD 5%; | 100% | 95%
DD-CD-UT-IT | - | Detailed | Included | Included | DD-CD-UT-IT.-.Detailed.Included.Included | 0% | 0% | 17% | 47% | 20% | 16% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Detailed | Included | Not-Included | DD-CD-UT-IT.-.Detailed.Included.Not-Included | 0% | 0% | 18% | 48% | 22% | 12% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Detailed | Not-Included | Included | DD-CD-UT-IT.-.Detailed.Not-Included.Included | 0% | 0% | 19% | 50% | 16% | 15% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Detailed | Not-Included | Not-Included | DD-CD-UT-IT.-.Detailed.Not-Included.Not-Included | 0% | 0% | 20% | 53% | 17% | 10% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Outline | Included | Included | DD-CD-UT-IT.-.Outline.Included.Included | 0% | 0% | 7% | 50% | 28% | 15% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Outline | Included | Not-Included | DD-CD-UT-IT.-.Outline.Included.Not-Included | 0% | 0% | 8% | 51% | 30% | 11% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Outline | Not-Included | Included | DD-CD-UT-IT.-.Outline.Not-Included.Included | 0% | 0% | 8% | 58% | 20% | 14% | 0% | Norm S1/2021 | 100% | 100%
DD-CD-UT-IT | - | Outline | Not-Included | Not-Included | DD-CD-UT-IT.-.Outline.Not-Included.Not-Included | 0% | 0% | 8% | 66% | 18% | 8% | 0% | Norm S1/2021 | 100% | 100%
CD-UT-IT | - | - | Included | Included | CD-UT-IT.-.-.Included.Included | 0% | 0% | 0% | 50% | 30% | 20% | 0% | Norm S1/2021 | 100% | 100%
CD-UT-IT | - | - | Included | Not-Included | CD-UT-IT.-.-.Included.Not-Included | 0% | 0% | 0% | 53% | 32% | 15% | 0% | Norm S1/2021 | 100% | 100%
CD-UT-IT | - | - | Not-Included | Included | CD-UT-IT.-.-.Not-Included.Included | 0% | 0% | 0% | 60% | 25% | 15% | 0% | Norm S1/2021 | 100% | 100%
CD-UT-IT | - | - | Not-Included | Not-Included | CD-UT-IT.-.-.Not-Included.Not-Included | 0% | 0% | 0% | 65% | 25% | 10% | 0% | Norm S1/2021 | 100% | 100%
CD-UT | - | - | Included | - | CD-UT.-.-.Included.- | 0% | 0% | 0% | 65% | 35% | 0% | 0% | Norm S1/2021 | 100% | 100%
CD-UT | - | - | Not-Included | - | CD-UT.-.-.Not-Included.- | 0% | 0% | 0% | 75% | 25% | 0% | 0% | Norm S1/2021 | 100% | 100%
Overhead Management Effort
Daily Report | Daily Meeting | Weekly Report | Weekly Meeting | Key | Key: %OVH
Yes | Yes | Yes | Yes | Yes.Yes.Yes.Yes | Key: 25%; %RQ: *1
Yes | No | Yes | Yes | Yes.No.Yes.Yes | Key: 22%; %RQ: *2
No | No | Yes | Yes | No.No.Yes.Yes | Key: 17%; %RQ: *3
No | No | Yes | No | No.No.Yes.No | Key: 15%; %RQ: *4
No | Yes | Yes | Yes | No.Yes.Yes.Yes | Key: 22%; %RQ: Refer No2
No | Yes | Yes | No | No.Yes.Yes.No | Key: 22%; %RQ: Refer No2
No | Yes | No | No | No.Yes.No.No | Key: 17%; %RQ: Refer No3
Yes | No | Yes | No | Yes.No.Yes.No | Key: 22%; %RQ: Refer No2
Yes | No | No | No | Yes.No.No.No | Key: 17%; %RQ: Refer No3
Tester Effort Rate | 70%
Language Conversion Rate for Coding Productivity
Development Languages | Productivity (LOC/MM) | Productivity (Adjusted)
Android | 2600 | 2600
C# | 2300 | 2300
C++ | 1900 | 1900
iOS | 2000 | 2000
JAVA | 1800 | 1800
JS | 2300 | 2300
PHP | 2800 | 2800
React Native | 2300 | 2300
VB | 2800 | 2800
.NET | 2000 | 2000
Xamarin | 1400 | 1400
Others | 2600 | 2600
Metrics for Complex Level
Complex Level | Complex Description (*1) |  |  |  | %UT: Coding Effort (*2); %IT: Coding Effort Adjusted (*3)
Very Simple | ~ Static content < 1 page A4 hoặc hiển thị single data < 5 items |  |  |  | %UT: 0.6; %IT: 0.6
Simple | Chức năng xử lý view data < 10 items |  |  |  | %UT: 1.4; %IT: 1.4
Average | Chức năng xử lý input/update/delete hoặc search simple < 10 items |  |  |  | %UT: 2; %IT: 2
Complex | Chức năng view/input/update/delete, hoặc search advance, có complex item (table/chart...) < 10 items |  |  |  | %UT: 3.3; %IT: 3.3
Very Complex | Chức năng có nghiệp vụ phức tạp, tổng hợp nhiều data |  |  |  | %UT: 6; %IT: 6

## GUIDELINE (hidden)
Estimation Guideline
1 | Complex Level Criteria
| Level | Criteria
| Very Simple | ~ Static content < 1 page A4 hoặc hiển thị single data < 5 items
| Simple | Chức năng xử lý view data < 10 items
| Average | Chức năng xử lý input/update/delete hoặc search simple < 10 items
| Complex | Chức năng view/input/update/delete, hoặc search advance, có complex item (table/chart...) < 10 items
| Very Complex | Chức năng có nghiệp vụ phức tạp, tổng hợp nhiều data
2 | LOC Estimation
Estimated LOC = <Average common LOC> + <#Screen Items>*<Average LOC for each Screen Item>
+ <#Logic Steps>*<Average LOC for each Logic Step>
+ <#Table Fields>*<Average LOC for each Table Field>
Coding Effort = <Estimated LOC> / <Productivity by language> * (1 - <%Reuse>) * 20
About <Average common LOC>, <Average LOC for each Factor Element>, <Productivity>, please refer [METRICS] sheet
3 | Adjustment Decision
| No | Non-Functional Requirement Factors |  | Adjustment Decision (*1) | Adjustment Rate (*1) | Adjustment Reasons
| 1.1 | Useability |  | Very High | 1.1 | Yêu cầu rất cao về tính thuận tiện/thẩm mỹ cho người dùng; Yêu cầu test UI/thao tác bổ sung với 5-8 môi trường.
| 1.2 |  |  | High | 1.05 | Yêu cầu cao về tính thuận tiện/thẩm mỹ cho người dùng; Yêu cầu test UI/thao tác bổ sung với 2-4 môi trường.
| 1.3 |  |  | Normal | 1 | Yêu cầu thông dụng (vd: focus on update, default value...); Yêu cầu test UI/thao tác bổ sung tối đa 1 môi trường.
| 1.4 |  |  | Low | 0.95 | Yêu cầu thấp, ưu tiên tính năng & ko yêu cầu về tính thuận tiện/thẩm mỹ, không hỗ trợ UI đa môi trường.
| 2.1 | Availability |  | High | 1.2 | Yêu cầu cao về khả năng đáp ứng của hệ thống, cần ưu tiên khi thiết kế, xây dựng (redundant, balancing)
| 2.2 |  |  | Normal | 1 | Yêu cầu thông thường, mặc định là nên có đối với 1 số phân hệ của hệ thống.
| 2.3 |  |  | Low | 0.9 | Yêu cầu thấp hoặc không bắt buộc.
| 3.1 | Performance |  | High | 1.1 | Yêu cầu rất cao về performance, mọi xử lý quan trọng phải ưu tiên số 1 về performance.
| 3.2 |  |  | Normal | 1 | Yêu cầu thông thường, mặc định (các xử lý quan trọng cần ưu tiên perfomance nhưng ko phải là ưu tiên cao nhất)
| 3.3 |  |  | Low | 0.9 | Yêu cầu thâp hoặc không bắt buộc phải có.
| 4.1 | Business Rule & Regulation |  | High | 1.1 | Yêu cầu cao (phân quyền đến mức dữ liệu, kiểm soát lịch sử truy cập, thống kê thao tác, theo dõi thao tác bất thường)
| 4.2 |  |  | Normal | 1 | Yêu cầu thông thường, mặc định (có tối thiểu phân quyền chức năng)
| 4.3 |  |  | Low | 0.9 | Yêu cầu thấp hoặc không bắt buộc.
| 5.1 | Technology Used |  | High | 1.2 | Yêu cầu công nghệ mới, ít phổ biến hoặc đặc thù riêng của khách hàng mà VIETIS ko quen thuộc
| 5.2 |  |  | Normal | 1 | Yêu cầu thông thường (công nghệ có sẵn)
| 5.3 |  |  | Low | 0.9 | Yêu cầu thấp, phổ thông, ít xử lý logic mà chủ yếu là config, kéo/thả do sự hỗ trợ sẵn có của Tool/Framework…
| 6.1 | Interface with other systems |  | Very High | 1.2 | > 40% chức năng/xử lý có liên quan đến hệ thống bên ngoài.
| 6.2 |  |  | High | 1.1 | > 20% đến 40% chức năng/xử lý có liên quan đến hệ thống bên ngoài.
| 6.3 |  |  | Normal | 1 | 1% đến 20% chức năng/xử lý liên quan đến tương tác với hệ thống bên ngoài
| 6.4 |  |  | Low | 0.95 | Không có tương tác với hệ thống ngoài.
4 | Internal Estimation
| Technology / Business | [5 empty] | Hệ số
| 1-Quen thuộc |  | Có ít nhất 25% member là BA/Techlead/Teamlead là master về công nghệ/business liên quan. |  |  |  | 1
| 2-Ít quen thuộc |  | Dưới 25% member là BA/Techlead/Teamlead là master về công nghệ/business liên quan. |  |  |  | 1.1
| 3-Chưa quen thuộc |  | Không có BA/Techlead/Teamlead là master về công nghệ/business liên quan. |  |  |  | 1.2
# | Resource Skill | [5 empty] | Hệ số
1 | Fresher (học việc, dưới 6 tháng kinh nghiệm) | [5 empty] | 1.2
2 | BA / Designer / Developer / Tester (Trên 6 tháng kinh nghiệm) | [5 empty] | 1
3 | BA Lead / Technical Leader | [5 empty] | 0.8
| Lưu ý: | (i) Số năm kinh nghiệm của Resource Skill #1 ~ #2 là thời gian làm dự án thực tế, ko theo công nghệ.
(ii) Số năm kinh nghiệm của Resource Skill #3 (Tech Lead) phụ thuộc vào công nghệ. Trường hợp trái công nghệ tính là Skill 2.